## Sheet1
IAS Dray Management Status
Sno | Module | Task | Status
1 | Login | Login page design | Completed
|  | Authentication check for user and admin | Completed
|  | Showing Error message for wrong credentials and validation | Completed
2 | Dashboard | Dashboard design and layout | Completed
|  | Listing all shipments | Completed
|  | Add comments for particular shipments | Completed
|  | Add docreceipt for particular shipments | Completed
|  | Add shipment with validation | InProgress
3 | Headers | Header design | Completed
|  | Show mail box according to user role | Completed
4 | View Comments | View comments design and listing | Pending
5 | Upload shipments | Upload shipments and listing | Pending
6 | Mail Inbox ,outbox,Compose | Mail inbox and outbox design | Pending
|  | Retrieving mail from kevin mail box | Pending
|  | Compose mail from kevin mail box | Pending